## Sheet1
feature | Description | State | Duration
Product component | Show list of product on the Home page | Open | 2 | Time | 26 | hr
Filter Component | Filter product based on their size and sort by price | Open | 2 | Rate | 500 | Rs/hr
cart Component | show selected items in the cart on the right sidebar | Open | 2 | cost | 13000 | rs
add animation | animated productlist and addind to cart | Open | 2
add modal | show modal when user click on a product | Open | 2
checkout form | show checkout form to get buyer data | Open | 2
product Backend | create simple backend to send product to frontend | Open | 2
Add Redux | create store, initial state and reducer and redux devtools | Open | 2
Add Redux to Product | move product state to redux | Open | 2
Add Redux to Filter | move filter state to redux | Open | 2
Add Redux to Cart | move cart state to redux | Open | 2
Create Order | handle frontend and backend of creating an order | Open | 2
Add Admin Section | use react router to create two routs for home and admin | Open | 2
Publish